## Schedule
				Hours remaining	Hours used	Dev hours total done by end of week
Date	Person	Hours		318	0
Sept 24-Sept 30	Sully	6
	Tech	6
	Shane	6
	Patrick	6
	Mike	6
	Anna	6	PM responsibilities	282	36	29
Oct 1-Oct 7	Sully	6
	Tech	6
	Shane	6
	Patrick	6
	Mike	6
	Anna	6	PM responsibilities	246	72	58
Oct 8-Oct 14	Sully	3	Midterm
	Tech	3	Midterm
	Shane	3	Midterm
	Patrick	6
	Mike	3	Midterm
	Anna	6	PM responsibilities	222	96	75
Oct 15-Oct 21	Sully	6
	Tech	6
	Shane	6
	Patrick	6
	Mike	6
	Anna	6	PM responsibilities	186	132	104
Oct 22-Oct 28	Sully	6
	Tech	6
	Shane	6
	Patrick	6
	Mike	6
	Anna	6	PM responsibilities	150	168	133
Oct 29-Nov 4	Sully	6
	Tech	6
	Shane	6
	Patrick	6
	Mike	6
	Anna	6	PM responsibilities	114	204	162		10	weeks
Nov 5-Nov 11	Sully	6						6	team members
	Tech	6						6	hours
	Shane	6						360	hours possible
	Patrick	6
	Mike	6						-12	midterm
	Anna	6	PM responsibilities	78	240	191		-30	Thanksgiving
Nov 12-Nov 18	Sully	6						318	billable hours	100	dollars per hour = $	31800	Cost to Customer
	Tech	6
	Shane	6						-10	Project Management (1 hour per week)
	Patrick	6						-60	Team meetings/reviews/communication
	Mike	6						248	hours available for development
	Anna	6	PM responsibilities	42	276	220
Nov 19-Nov 25	Sully	1	Thanksgiving
	Tech	1	Thanksgiving
	Shane	1	Thanksgiving
	Patrick	1	Thanksgiving
	Mike	1	Thanksgiving
	Anna	1	PM responsibilities	36	282	219
Nov 26-Dec 2	Sully	6
Last week!	Tech	6
	Shane	6
	Patrick	6
	Mike	6
	Anna	6	PM responsibilities	0	318	248
Dec 3: Presentation
Total hours:		318	hours

## Wave 1
1.2	Wave 1	GUI min time	GUI exp time	GUI max time	GUI time	Person Responsible	Logic min time	Logic exp time	Logic max time	Logic time	Total time	Person Responsible	Dependencies
1.2.1	Database				0	Sully	3.5	5.5	8.5	5.67	5.67
1.2.2	Employee Login				2.17	Tech				4.17	6.33		1.2.1
1.2.2.1	Process Login	0.5	1	2	1.08		1.25	1.5	3	1.71
1.2.2.2	Populate task nav bar	0.5	1	2	1.08		1	1	2.5	1.25
1.2.2.3	Encryption	0	0	0	0		1	1	2.25	1.21
1.2.3	Browse Products				4.5	Tech				8.17	12.67		1.2.1
1.2.3.1	Side category bar	0.75	1.25	2.5	1.38		2	3.25	4	3.17
1.2.3.2	View specific product	1	1.5	3	1.67		2	2.5	3	2.5
1.2.3.3	View multiple products	0.75	1.25	3	1.46		2	2.5	3	2.5
1.2.4	Shopping Cart				5.17	Patrick				7.04	12.21		1.2.3
1.2.4.1	Add to cart	0.5	0.75	1.25	0.79		2	3	4	3
1.2.4.2	Show cart	1.5	2	2.75	2.04		1.5	2.5	3.5	2.5
1.2.4.3	Modify cart	0.5	1	2.5	1.17		1	1.5	2.25	1.54
1.2.4.4	Update cart contents count	0.5	1	2.5	1.17		1	1.5	2.5	1.58
1.2.5	Make purchase				4.83	Patrick				13.5	18.33		1.2.4
1.2.5.1	Process customer info	1	1.75	4	2		3	4.5	6	4.5
1.2.5.2	Process payment info	1	1.75	4	2		3	4.5	6	4.5
1.2.5.3	Update inventory	0	0	0	0		2	3	4	3
1.2.5.4	Confirm order	0.5	0.75	1.5	0.83		1	1.5	2	1.5
1.2.6	Help system				5.71	Tech				6.75	12.46		1.2.1
1.2.6.1	Company info	0.5	1.5	2	1.42		1	1	2	1.17
1.2.6.2	FAQ	1.5	3	3.5	2.83		1	2	3.5	2.08
1.2.6.3	Email form	0.75	1.5	2	1.46		2	3.5	5	3.5
1.2.7	Manage inventory	2	4	6	4	Patrick	3	5	8	5.17	9.17		1.2.1
1.2.8	Form verification	0.5	1.5	3	1.58	Patrick	1.5	2.5	4	2.58	4.17
1.2.9	Metrics	2	4	6	4	Tech	2.5	4	6	4.08	8.08		1.2.1
1.2.10	Test				6.48					9.06	15.54
1.2.10.1	Login	0.25	0.5	1	0.54	Mike	0.5	1	1.5	1		Mike	1.2.2
1.2.10.2	Browse	0.5	1	1.5	1	Anna	0.75	1	1.25	1		Anna	1.2.3
1.2.10.3	Shopping Cart	0.75	1	2	1.13	Mike	0.75	1.25	2	1.29		Mike	1.2.4
1.2.10.4	Make purchase	0.5	0.75	2	0.92	Anna	0.75	1	1.5	1.04		Anna	1.2.5
1.2.10.5	Help system	0.1	0.25	0.5	0.27	Anna	0.5	0.75	1.5	0.83		Anna	1.2.6
1.2.10.6	Manage inventory	0.5	0.75	2	0.92	Mike	1.75	2	2.5	2.04		Mike	1.2.7
1.2.10.7	Form verification	0.25	0.5	0.75	0.5	Mike	0.25	0.5	1.12	0.56		Mike	1.2.8
1.2.10.8	Metrics	0.75	1	2.5	1.21	Mike	0.75	1.25	2	1.29		Mike	1.2.9
1.2.11	Defects										26.73			Defect time equal to 20% of development time

										Total Hours	131.35

									Remaining hours	116.66

## Wave 2
1.3	Wave 2	GUI min time	GUI exp time	GUI max time	GUI time	Person Responsible	Logic min time	Logic exp time	Logic max time	Logic time	Total time	Person Responsible	Dependencies
1.3.1	Search	0.5	1	2	1.08		2.5	4.5	6	4.42	18.5
1.3.2	Sales				5.5					10.25	15.75
1.3.2.1	Place on sale	1	2	3.5	2.08		1.5	3	4	2.92
1.3.2.2	Display sale	0.5	1.5	3	1.58		1	2	3.5	2.08
1.3.2.3	Remove from sale	0.5	0.75	1	0.75		1	2	3.5	2.08
1.3.2.4	Query all sale items	0.5	1	2	1.08		2	3	5	3.17
1.3.3	Shipping				4.67					6.75	11.42
1.3.3.1	Query all orders	1	2	3.5	2.08		2	3	4.5	3.08
1.3.3.2	Query specific order	0.75	2	3.5	2.04		1.5	2	3	2.08
1.3.3.3	Mark item as shipped	0.25	0.5	1	0.54		1	1.5	2.5	1.58
1.3.4	Test				3.88					4	7.88
1.3.4.1	Search	0.5	0.75	1.25	0.79	Mike	0.75	1	1.25	1		Mike	1.3.1
1.3.4.2	Sales	1	1.5	2.5	1.58	Anna	1	1.5	2	1.5		Anna	1.3.2
1.3.4.3	Shipping	1	1.5	2	1.5	Mike	1	1.5	2	1.5		Mike	1.3.3
1.3.5	Defects										13.7

										Total Hours	67.24

									Wave 1 + Wave 2		198.59
									Remaining hours		49.41

## Wave 3
1.4	Wave 3	GUI min time	GUI exp time	GUI max time	GUI time	Logic min time	Logic exp time	Logic max time	Logic time	Total time	Dependencies
1.4.1	Customer Accounts				10.42				13.38	23.79
1.4.1.1	Create	0.5	2	3	1.92	2	3	4.25	3.04
1.4.1.2	Modify	0.5	2	3	1.92	1	2	3.5	2.08
1.4.1.3	Delete	0.5	1.5	3	1.58	1	1.5	2.5	1.58
1.4.1.4	View purchase history	1	2	3.5	2.08	1	2	3.5	2.08
1.4.1.5	Wish List				2.92				4.58
1.4.1.5.1	View	0.75	1.25	3	1.46	1.5	2.5	3.5	2.5
1.4.1.5.2	Modfy	0.75	1.25	3	1.46	1	2	3.5	2.08
1.4.2	Create new employee account	0.5	2	3	1.92	2	3	4.25	3.04	4.96
1.4.3	Modify employee account	0.5	2	3	1.92	1	2	3.5	2.08	4
1.4.4	Test				5.58				5.33	10.92
1.4.4.1	Customer accounts	0.75	2	3	1.96	1	2	3	2
1.4.4.2	Create employee account	1	2.25	3	2.17	1	2	3	2
1.4.4.3	Modify employee account	0.75	1.5	2	1.46	1	1.25	2	1.33
1.4.5	Defects									9.83

									Total Hours	53.49

								Wave 1 + Wave 2 + Wave 3		252.08
								Remaining hours		-4.08

## Wave 4
1.5	Wave 4	GUI min time	GUI exp time	GUI max time	GUI time	Logic min time	Logic exp time	Logic max time	Logic time	Total time	Dependencies
1.5.1	Reviews				5.25				10.58	15.83
1.5.1.1	Create	0.5	2	3.5	2	2.5	3.5	5	3.58
1.5.1.2	Sort				2.17				4.92
1.5.1.2.1	Rating	0.5	1	2	1.08	1.5	2.5	3.25	2.46
1.5.1.2.2	Date	0.5	1	2	1.08	1.5	2.5	3.25	2.46
1.5.1.3	Delete	0.5	1	2	1.08	1	2	3.5	2.08
1.5.2	Ratings				4.25				5.17	9.42
1.5.2.1	Leave a rating	1	2	3.5	2.67	2	3	4.5	3.63
1.5.2.2	Sort products by rating	0.5	1.5	3	1.58	1	1.5	2.25	1.54
1.5.3	Cancel orders	0.5	1	2	1.08	1.5	2	3	2.08	3.17
1.5.4	Return items	1	2	3.5	2.08	1.5	2	3	2.08	4.17
1.5.5	Email all account holders	0.25	1	1.5	0.96	1.5	2.5	4	2.58	3.54
1.5.6	View tracking about site stats	1	1.5	3	1.67	2	3.5	5	3.5	5.17
1.5.7	Report tracking # for shipments	0.5	1.25	2	1.25	2	3.5	5	3.5	4.75
1.5.8	Test				10.63				10.54	21.17
	Reviews	0.5	1.5	2.5	1.5	0.5	1.25	2	1.25
	Ratings	0.5	1	1.5	1	0.5	1.25	2	1.25
	Cancel orders	1.5	2.25	3	2.25	1.25	2.25	3.25	2.25
	Return items	0.75	1.75	2.5	1.71	1	2	3	2
	Email all account holders	0.5	1	1.5	1	0.5	1.25	1.75	1.21
	View tracking about site	1.5	2	3.25	2.13	0.75	1.25	2.25	1.33
	Report tracking # for shipments	0.75	1	1.5	1.04	0.5	1.25	2	1.25
1.5.9	Defects									10.84

									Total Hours	78.05

								Waves 1 + 2 + 3 + 4		330.12
								Remaining hours		-82.12

## Chart
Week start	Projected	Projected points used	Actual	Actual points used
09/24/12	248	0	248
10/01/12	219	29
10/08/12	190	58
10/15/12	173	75
10/22/12	144	104
10/29/12	115	133
11/05/12	86	162
11/12/12	57	191
11/19/12	28	220
11/26/12	29	220
12/03/12	0	248
Week / Points